## Summary
Unified Healthcare SaaS — Wave 1 Executable Feature Backlog v1.0
Metric | Value
Wave-1 requirements | 130
Epics | 8
Planned sprints | 5
Target vertical slice | Patient → appointment → encounter → clinical/order/medication → billing
Sprint | Primary Scope | Requirement Count
Sprint 1 | EMPI foundation | 9
Sprint 2 | EMPI completion | 9
Sprint 3 | Scheduling | 16
Sprint 4 | Encounter + Clinical + Nursing | 54
Sprint 5 | Orders + Medication + Billing | 42

## Wave 1 Backlog
Epic ID | Canonical Family | Feature Group | Feature ID | Story ID | Sprint | Requirement ID | Priority | Actor | Requirement | Acceptance Criterion | Dependencies | Bounded Context | Primary Service | Permission | Verification Profile | Criticality | Owner | DOR Status | Backlog Status | Estimate (SP) | Notes
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-001 | Sprint 1 | SRS-EMPI-001 | MUST | Registration | Create a patient with demographic minimum set configured by jurisdiction/facility. | Unique patient_id created; MRN assigned according to facility policy. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.create | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Identifier lifecycle | FEAT-W1-EMPI-IDENTIFIER-LIFECYCLE | STORY-SRS-EMPI-002 | Sprint 1 | SRS-EMPI-002 | MUST | System | Separate immutable internal patient_id from MRN/external identifiers. | MRN change/merge does not change internal patient_id. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Patient search | FEAT-W1-EMPI-PATIENT-SEARCH | STORY-SRS-EMPI-003 | Sprint 1 | SRS-EMPI-003 | MUST | Registration | Search before create using exact and fuzzy demographic match. | Potential duplicates are shown with confidence and protected fields masked by role. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.read | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Duplicate detection & match | FEAT-W1-EMPI-DUPLICATE-DETECTION-MATC | STORY-SRS-EMPI-004 | Sprint 1 | SRS-EMPI-004 | MUST | System | Calculate configurable duplicate confidence using name, phone, DOB/age, sex, address, government/health identifiers and prior identifiers. | Thresholds route to auto-clear, warning or manual-review states; no unsafe auto-merge. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Patient merge/unmerge | FEAT-W1-EMPI-PATIENT-MERGE-UNMERGE | STORY-SRS-EMPI-005 | Sprint 1 | SRS-EMPI-005 | MUST | Authorized HIM | Merge duplicate patient identities only through reviewed merge workflow. | All child references resolve to survivor; merge provenance preserved. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.read | VP-PLT | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Patient merge/unmerge | FEAT-W1-EMPI-PATIENT-MERGE-UNMERGE | STORY-SRS-EMPI-006 | Sprint 1 | SRS-EMPI-006 | MUST | Authorized HIM | Support controlled unmerge when technically safe and maintain provenance. | Unmerge restores ownership based on merge journal, or blocks with explicit reason. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.merge | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-007 | Sprint 1 | SRS-EMPI-007 | MUST | Registration | Maintain aliases, prior names, multiple phones/emails/addresses and communication preferences. | History is effective-dated and auditable. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-008 | Sprint 1 | SRS-EMPI-008 | MUST | System | Support deceased status with date/source and restrictions on routine scheduling. | New routine appointment warns/blocks per policy. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Related person / caregiver | FEAT-W1-EMPI-RELATED-PERSON-CAREGIVER | STORY-SRS-EMPI-009 | Sprint 1 | SRS-EMPI-009 | MUST | Registration | Capture guardian/caregiver relationship with authority/expiry where relevant. | Caregiver access honors relationship scope and expiry. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-010 | Sprint 2 | SRS-EMPI-010 | MUST | System | Support patient photo with consent/configuration and prohibit using photo as sole identity proof. | Identity workflow always includes configured positive identifiers. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Identifier lifecycle | FEAT-W1-EMPI-IDENTIFIER-LIFECYCLE | STORY-SRS-EMPI-011 | Sprint 2 | SRS-EMPI-011 | MUST | Integration | Link ABHA and other external patient identifiers through adapter without making them database primary keys. | Link/unlink history and source retained. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-012 | Sprint 2 | SRS-EMPI-012 | MUST | System | Detect demographic conflict from external sources and route to reconciliation instead of overwriting trusted data silently. | Conflicting value stored as proposed/source value until resolved. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-013 | Sprint 2 | SRS-EMPI-013 | MUST | Privacy User | Record patient communication and privacy preferences distinct from clinical consent. | Notification service checks current preference before optional communications. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.write | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-014 | Sprint 2 | SRS-EMPI-014 | MUST | System | Record sensitive demographic data with field-level access where configured. | Restricted fields are masked and read is audited. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.configure | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Patient merge/unmerge | FEAT-W1-EMPI-PATIENT-MERGE-UNMERGE | STORY-SRS-EMPI-015 | Sprint 2 | SRS-EMPI-015 | SHOULD | Registration | Support temporary/unknown patient registration for emergency use with later identity reconciliation. | Temporary record can be converted/merged without losing encounter chronology. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.merge | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Duplicate detection & match | FEAT-W1-EMPI-DUPLICATE-DETECTION-MATC | STORY-SRS-EMPI-016 | Sprint 2 | SRS-EMPI-016 | MUST | System | Prevent duplicate MRN assignment under concurrent registration. | Concurrency test produces unique values. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.sign | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Enterprise Master Patient Index | FEAT-W1-EMPI-ENTERPRISE-MASTER-PATIEN | STORY-SRS-EMPI-017 | Sprint 2 | SRS-EMPI-017 | MUST | Patient/Admin | Support data correction request workflow without erasing clinical record provenance. | Approved correction updates demographic master and retains prior value/history. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.write | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-EMPI | SRS-EMPI | Patient merge/unmerge | FEAT-W1-EMPI-PATIENT-MERGE-UNMERGE | STORY-SRS-EMPI-018 | Sprint 2 | SRS-EMPI-018 | MUST | System | Create patient.created, patient.demographics_updated, patient.merged and patient.deceased events. | Events include tenant/patient/version/correlation metadata only as necessary. | Wave 0 tenant/IAM/API/data/security foundation | patient.identity | PatientService | empi.create | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Availability / slot management | FEAT-W1-SCH-AVAILABILITY-SLOT-MANAGE | STORY-SRS-SCH-001 | Sprint 3 | SRS-SCH-001 | MUST | Scheduler | Define provider/resource schedules with facility, department, visit type, slot duration, capacity and effective dates. | Slot search reflects active roster and exceptions. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Scheduling, Appointments and Queue | FEAT-W1-SCH-SCHEDULING-APPOINTMENTS- | STORY-SRS-SCH-002 | Sprint 3 | SRS-SCH-002 | MUST | Scheduler | Create leave/block/meeting/OT/procedure exceptions. | Blocked capacity cannot be booked unless override permission. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.create | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Availability / slot management | FEAT-W1-SCH-AVAILABILITY-SLOT-MANAGE | STORY-SRS-SCH-003 | Sprint 3 | SRS-SCH-003 | MUST | Patient/Staff | Search available slots by specialty, provider, facility, visit type, date range and mode. | Only bookable capacity is returned; response is paginated. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.read | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Booking | FEAT-W1-SCH-BOOKING | STORY-SRS-SCH-004 | Sprint 3 | SRS-SCH-004 | MUST | Patient/Staff | Book appointment atomically and prevent overbooking beyond configured capacity. | Concurrent booking test does not exceed capacity. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.configure | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Cancellation / no-show | FEAT-W1-SCH-CANCELLATION-NO-SHOW | STORY-SRS-SCH-005 | Sprint 3 | SRS-SCH-005 | MUST | Patient/Staff | Reschedule/cancel with policy-driven cutoff, reason and fee/refund integration. | Original appointment retains status history. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.cancel | VP-INT | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Waitlist / queue | FEAT-W1-SCH-WAITLIST-QUEUE | STORY-SRS-SCH-006 | Sprint 3 | SRS-SCH-006 | SHOULD | System | Operate waitlist and offer earlier slot according to rules. | Offer has expiry and cannot create duplicate confirmed bookings. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Scheduling, Appointments and Queue | FEAT-W1-SCH-SCHEDULING-APPOINTMENTS- | STORY-SRS-SCH-007 | Sprint 3 | SRS-SCH-007 | MUST | Registration | Check in patient and issue token/queue state. | Check-in timestamp and arrival mode recorded. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Waitlist / queue | FEAT-W1-SCH-WAITLIST-QUEUE | STORY-SRS-SCH-008 | Sprint 3 | SRS-SCH-008 | MUST | System | Maintain queue states: scheduled, arrived, triaged, waiting clinician, in consultation, post-consultation, completed, no-show, cancelled. | Transitions reject invalid sequence unless authorized correction. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Waitlist / queue | FEAT-W1-SCH-WAITLIST-QUEUE | STORY-SRS-SCH-009 | Sprint 3 | SRS-SCH-009 | SHOULD | System | Estimate waiting time using current service rate, queue and provider status. | Estimate labeled as estimate and updates without changing clinical priority. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Scheduling, Appointments and Queue | FEAT-W1-SCH-SCHEDULING-APPOINTMENTS- | STORY-SRS-SCH-010 | Sprint 3 | SRS-SCH-010 | MUST | Staff | Support walk-in appointment/queue with reason and prioritization policy. | Walk-in is linked to same encounter creation flow. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Scheduling, Appointments and Queue | FEAT-W1-SCH-SCHEDULING-APPOINTMENTS- | STORY-SRS-SCH-011 | Sprint 3 | SRS-SCH-011 | MUST | Clinical Staff | Allow medically justified queue reprioritization with reason. | Reprioritization is audited and visible to queue users. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Cancellation / no-show | FEAT-W1-SCH-CANCELLATION-NO-SHOW | STORY-SRS-SCH-012 | Sprint 3 | SRS-SCH-012 | MUST | System | Send configurable booking/reminder/reschedule/cancellation notifications. | Notification delivery outcome recorded. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Scheduling, Appointments and Queue | FEAT-W1-SCH-SCHEDULING-APPOINTMENTS- | STORY-SRS-SCH-013 | Sprint 3 | SRS-SCH-013 | SHOULD | Admin | Support recurring appointments/therapy series. | Series changes can affect one occurrence or future occurrences. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Booking | FEAT-W1-SCH-BOOKING | STORY-SRS-SCH-014 | Sprint 3 | SRS-SCH-014 | MUST | System | Prevent booking inactive provider/resource/facility. | API returns domain-specific unavailability error. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Scheduling, Appointments and Queue | FEAT-W1-SCH-SCHEDULING-APPOINTMENTS- | STORY-SRS-SCH-015 | Sprint 3 | SRS-SCH-015 | SHOULD | Admin | Configure teleconsult vs in-person appointment rules. | Visit mode drives location/link and eligibility checks. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.configure | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-SCH | SRS-SCH | Cancellation / no-show | FEAT-W1-SCH-CANCELLATION-NO-SHOW | STORY-SRS-SCH-016 | Sprint 3 | SRS-SCH-016 | MUST | System | Emit appointment.booked/rescheduled/cancelled/checked_in/no_show events. | Events are idempotent/versioned. | Wave 0 tenant/IAM/API/data/security foundation; provider/resource master | scheduling | AppointmentService | sch.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-001 | Sprint 4 | SRS-ENC-001 | MUST | System/Clinician | Create encounter linked to patient, facility, service, visit type, attending/primary provider and reason. | Encounter_id unique and state begins valid for context. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.create | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-002 | Sprint 4 | SRS-ENC-002 | MUST | System | Support OPD, emergency, inpatient, day-care, telemedicine, home-care and diagnostic-only encounter classes. | Class-specific rules derive from common encounter model. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.merge | VP-UX | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-003 | Sprint 4 | SRS-ENC-003 | MUST | Clinician | Start/end clinical encounter with timestamps independent of appointment status. | Appointment and encounter remain separately auditable. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Episode of care | FEAT-W1-ENC-EPISODE-OF-CARE | STORY-SRS-ENC-004 | Sprint 4 | SRS-ENC-004 | MUST | System | Support episode-of-care grouping for longitudinal treatment such as pregnancy, oncology or dialysis. | Multiple encounters can reference one episode without copying data. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter and Episode Management | FEAT-W1-ENC-ENCOUNTER-AND-EPISODE-MA | STORY-SRS-ENC-005 | Sprint 4 | SRS-ENC-005 | MUST | Clinical User | Assign care team members with role and effective time. | Authorization can evaluate active care-team relationship. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.sign | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-006 | Sprint 4 | SRS-ENC-006 | MUST | System | Maintain encounter status transitions with explicit cancellation/entered-in-error semantics. | Invalid state change rejected. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-007 | Sprint 4 | SRS-ENC-007 | MUST | Clinical User | Capture encounter diagnoses with type (provisional/final/primary/secondary) and coding system. | Diagnosis history and author/time retained. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-008 | Sprint 4 | SRS-ENC-008 | MUST | System | Prevent finalization of encounter if configured mandatory documentation is incomplete, with emergency override where policy allows. | Blocking items listed; override reason audited. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.configure | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-009 | Sprint 4 | SRS-ENC-009 | MUST | Clinician | Close encounter and generate visit summary from signed data; later changes require amendment/addendum. | Closed encounter chronology cannot be silently rewritten. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.sign | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter and Episode Management | FEAT-W1-ENC-ENCOUNTER-AND-EPISODE-MA | STORY-SRS-ENC-010 | Sprint 4 | SRS-ENC-010 | SHOULD | System | Support linked external referral/request source. | Referral can be closed-looped on completion. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter and Episode Management | FEAT-W1-ENC-ENCOUNTER-AND-EPISODE-MA | STORY-SRS-ENC-011 | Sprint 4 | SRS-ENC-011 | MUST | System | Expose longitudinal timeline query with purpose/permission filtering. | Unauthorized restricted notes are omitted/masked. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.manage | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ENC | SRS-ENC | Encounter lifecycle | FEAT-W1-ENC-ENCOUNTER-LIFECYCLE | STORY-SRS-ENC-012 | Sprint 4 | SRS-ENC-012 | MUST | System | Emit encounter.started/completed/cancelled and diagnosis.recorded events. | Event ordering/version is deterministic per aggregate. | Wave 0 tenant/IAM/API/data/security foundation; Patient/EMPI | encounter | EncounterService | enc.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Allergy | FEAT-W1-CLN-ALLERGY | STORY-SRS-CLN-001 | Sprint 4 | SRS-CLN-001 | MUST | Clinician | Display patient banner with positive identifiers, age/sex, allergies, major alerts and encounter context. | Banner persists on clinical screens and patient switch is visually explicit. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical documentation | FEAT-W1-CLN-CLINICAL-DOCUMENTATION | STORY-SRS-CLN-002 | Sprint 4 | SRS-CLN-002 | MUST | Clinician | Document structured and narrative notes using versioned specialty/general templates. | Saved note references exact template version. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Problem list | FEAT-W1-CLN-PROBLEM-LIST | STORY-SRS-CLN-003 | Sprint 4 | SRS-CLN-003 | MUST | Clinician | Maintain problem list with status, onset, resolution and coded diagnosis mapping. | Resolved problem remains historical. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Allergy | FEAT-W1-CLN-ALLERGY | STORY-SRS-CLN-004 | Sprint 4 | SRS-CLN-004 | MUST | Clinician | Record allergy/intolerance with substance, reaction, severity, certainty and verification status. | Allergy is available to medication decision support immediately after commit. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.write | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Observation / vital | FEAT-W1-CLN-OBSERVATION-VITAL | STORY-SRS-CLN-005 | Sprint 4 | SRS-CLN-005 | MUST | Clinician | Record observations with code, value, unit, reference/interpretation, time, performer, device/source and status. | Trend query retains original unit/source and normalized representation if available. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.write | VP-INT | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-006 | Sprint 4 | SRS-CLN-006 | MUST | Clinician | Create procedure record with indication, performer, site/laterality, outcome, complications and linked orders. | Procedure can reference implants/specimens without duplicating master data. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.create | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Problem list | FEAT-W1-CLN-PROBLEM-LIST | STORY-SRS-CLN-007 | Sprint 4 | SRS-CLN-007 | MUST | Clinician | Create care plans containing problems, goals, interventions, owners, target dates and status. | Tasks can link to care-plan activity. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.create | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical document signing | FEAT-W1-CLN-CLINICAL-DOCUMENT-SIGNIN | STORY-SRS-CLN-008 | Sprint 4 | SRS-CLN-008 | MUST | System | Support clinical document lifecycle draft → signed/final → amended/addendum/entered-in-error with permissions. | Signed content cannot be edited in-place. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.sign | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical document signing | FEAT-W1-CLN-CLINICAL-DOCUMENT-SIGNIN | STORY-SRS-CLN-009 | Sprint 4 | SRS-CLN-009 | MUST | Clinician | Sign clinical document with authenticated identity, timestamp and signature meaning. | Signature metadata and content hash/version retained. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.sign | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-010 | Sprint 4 | SRS-CLN-010 | MUST | System | Maintain provenance for imported/external records including source organization/system and ingestion time. | External data is distinguishable from locally authored data. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.import | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Observation / vital | FEAT-W1-CLN-OBSERVATION-VITAL | STORY-SRS-CLN-011 | Sprint 4 | SRS-CLN-011 | MUST | System | Show result/observation abnormal/critical flags supplied by authoritative diagnostic service; UI must not infer criticality independently. | Flag provenance visible. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-012 | Sprint 4 | SRS-CLN-012 | MUST | Clinician | Acknowledge configured critical result alerts with timestamp and action/comment. | Unacknowledged alerts escalate according to policy. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.configure | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-013 | Sprint 4 | SRS-CLN-013 | MUST | Clinician | Record consents and procedure-specific consent references without conflating with privacy consents. | Clinical action checks required consent where configured. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.write | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-014 | Sprint 4 | SRS-CLN-014 | MUST | Clinician | Support attachments/images with type, source, timestamp and confidentiality class. | Attachment access follows parent record and classification. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-015 | Sprint 4 | SRS-CLN-015 | SHOULD | Clinician | Use smart phrases/macros with user-visible expansion and no hidden clinical text. | Final signed note stores expanded text/provenance. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-016 | Sprint 4 | SRS-CLN-016 | SHOULD | Clinician | Use voice/dictation integration as draft input. | Clinician must review/sign resulting note; original audio retention configurable. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-INT | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-017 | Sprint 4 | SRS-CLN-017 | MUST | System | Maintain patient-context lock and warning when opening multiple patient charts simultaneously. | Medication/order action clearly identifies target patient and encounter. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical documentation | FEAT-W1-CLN-CLINICAL-DOCUMENTATION | STORY-SRS-CLN-018 | Sprint 4 | SRS-CLN-018 | MUST | System | Provide chronological timeline filters for encounters, meds, labs, imaging, diagnoses, procedures and documents. | Filters never change underlying record. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-019 | Sprint 4 | SRS-CLN-019 | MUST | System | Support confidential/restricted note class with narrower role/purpose authorization. | Restricted-note read is explicitly audited. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-020 | Sprint 4 | SRS-CLN-020 | MUST | System | Ensure clinical calculators are versioned and store input values, formula/version, output, units and interpretation. | Recalculation with new formula never overwrites historical result. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-021 | Sprint 4 | SRS-CLN-021 | MUST | System | CDS alerts must identify triggering rule/version and allow configured override reason. | Override is stored and reportable. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.configure | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-022 | Sprint 4 | SRS-CLN-022 | MUST | Clinician | Support referral/consult request with specialty, urgency, reason and requested question. | Consult response closes loop and remains linked. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Clinical Core | FEAT-W1-CLN-CLINICAL-CORE | STORY-SRS-CLN-023 | Sprint 4 | SRS-CLN-023 | MUST | System | Support longitudinal disease registry references without copying entire chart. | Registry membership points to canonical clinical facts. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-CLN | SRS-CLN | Allergy | FEAT-W1-CLN-ALLERGY | STORY-SRS-CLN-024 | Sprint 4 | SRS-CLN-024 | MUST | System | Emit clinical_document.signed, observation.recorded, problem.updated, allergy.updated, procedure.completed and critical_result.acknowledged events. | Events contain minimum necessary data and references. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; terminology binding | clinical.core | ClinicalService | cln.update | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing assessment | FEAT-W1-NUR-NURSING-ASSESSMENT | STORY-SRS-NUR-001 | Sprint 4 | SRS-NUR-001 | MUST | Nurse | Perform admission/initial nursing assessment using versioned age/service-specific template. | Assessment author/time/template version retained. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-002 | Sprint 4 | SRS-NUR-002 | MUST | Nurse | Create/update nursing care plan with problems, goals, interventions, frequency and evaluation. | Care plan tasks appear in nursing worklist. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.create | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Flowsheet | FEAT-W1-NUR-FLOWSHEET | STORY-SRS-NUR-003 | Sprint 4 | SRS-NUR-003 | MUST | Nurse | Record vitals and repeated observations in flowsheet with source and timestamp. | Late entry is identified as late and includes actual observation time. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.write | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-004 | Sprint 4 | SRS-NUR-004 | MUST | Nurse | Record intake/output by category with running shift/day balance. | Corrections use amendment trail. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.write | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-005 | Sprint 4 | SRS-NUR-005 | MUST | Nurse | Assess fall, pressure injury, pain and other configured risk scores. | Score version and inputs stored; due reassessment appears as task. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.configure | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-006 | Sprint 4 | SRS-NUR-006 | MUST | Nurse | Maintain lines/tubes/drains/catheters with insertion, site, care, output and removal. | Device-days can be calculated from canonical dates. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | eMAR | FEAT-W1-NUR-EMAR | STORY-SRS-NUR-007 | Sprint 4 | SRS-NUR-007 | MUST | Nurse | Receive medication administration schedule from medication service/eMAR. | Only active verified orders create administration tasks. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Medication administration | FEAT-W1-NUR-MEDICATION-ADMINISTRATIO | STORY-SRS-NUR-008 | Sprint 4 | SRS-NUR-008 | MUST | Nurse | Perform positive patient identification and medication verification before administration where barcode workflow enabled. | Mismatch prevents completion unless explicit emergency override policy. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-009 | Sprint 4 | SRS-NUR-009 | MUST | Nurse | Record administered/not-administered/held/refused/delayed with dose/time/route/site and reason. | MAR retains scheduled versus actual values. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.write | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Handover | FEAT-W1-NUR-HANDOVER | STORY-SRS-NUR-010 | Sprint 4 | SRS-NUR-010 | MUST | Nurse | Perform shift handover with structured outstanding issues, critical risks, devices and pending tasks. | Handover acknowledgement and shift are recorded. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-INT | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing task | FEAT-W1-NUR-NURSING-TASK | STORY-SRS-NUR-011 | Sprint 4 | SRS-NUR-011 | MUST | Nurse | Create nursing tasks with priority, due time, recurrence and completion evidence. | Overdue critical tasks escalate. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.create | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing assessment | FEAT-W1-NUR-NURSING-ASSESSMENT | STORY-SRS-NUR-012 | Sprint 4 | SRS-NUR-012 | MUST | Nurse | Document wound/skin assessment with location/body map and image where consented. | Images are versioned and access-controlled. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-013 | Sprint 4 | SRS-NUR-013 | MUST | Nurse | Document restraints with indication, authorization, monitoring and discontinuation. | Expired authorization triggers alert according to policy. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-014 | Sprint 4 | SRS-NUR-014 | MUST | Nurse | Record transfusion monitoring observations linked to blood-product episode. | Reaction action can be initiated from bedside workflow. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.write | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-015 | Sprint 4 | SRS-NUR-015 | MUST | Nurse | Document patient/family education and discharge readiness. | Education topic, learner, method and understanding status stored. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.read | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-016 | Sprint 4 | SRS-NUR-016 | SHOULD | Nurse Manager | View acuity/workload dashboard by unit. | Dashboard uses defined acuity inputs and never silently alters staffing decisions. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.read | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Nursing Core | FEAT-W1-NUR-NURSING-CORE | STORY-SRS-NUR-017 | Sprint 4 | SRS-NUR-017 | MUST | System | Support nurse assignment by unit/bed and care relationship. | Assignment changes are effective-dated and auditable. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.sign | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-NUR | SRS-NUR | Medication administration | FEAT-W1-NUR-MEDICATION-ADMINISTRATIO | STORY-SRS-NUR-018 | Sprint 4 | SRS-NUR-018 | MUST | System | Provide downtime-safe printable/edge workflows for medication and critical nursing tasks per deployment profile. | Recovery reconciliation prevents duplicate administration records. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core | nursing | NursingService | nur.manage | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order placement | FEAT-W1-ORD-ORDER-PLACEMENT | STORY-SRS-ORD-001 | Sprint 5 | SRS-ORD-001 | MUST | Clinician | Place laboratory, imaging, medication, procedure, diet, nursing, blood product, referral and allied-health orders through common order framework. | Each order has order_id, type, requester, patient, encounter, priority, status and target service. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order lifecycle | FEAT-W1-ORD-ORDER-LIFECYCLE | STORY-SRS-ORD-002 | Sprint 5 | SRS-ORD-002 | MUST | System | Validate order against patient/encounter state, requester privilege and required fields before acceptance. | Invalid request returns structured field/domain errors. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order sets | FEAT-W1-ORD-ORDER-SETS | STORY-SRS-ORD-003 | Sprint 5 | SRS-ORD-003 | MUST | Clinician | Use order sets with individually selectable components and visible defaults. | Order set version/provenance stored on resulting orders. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order cancellation | FEAT-W1-ORD-ORDER-CANCELLATION | STORY-SRS-ORD-004 | Sprint 5 | SRS-ORD-004 | MUST | Clinician | Modify/cancel only according to downstream execution status and domain policy. | Cancellation after execution is rejected or converted to appropriate downstream corrective workflow. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order cancellation | FEAT-W1-ORD-ORDER-CANCELLATION | STORY-SRS-ORD-005 | Sprint 5 | SRS-ORD-005 | MUST | System | Maintain order state requested → accepted → scheduled/in-progress → completed or cancelled/entered-in-error. | Transitions are domain-validated. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order lifecycle | FEAT-W1-ORD-ORDER-LIFECYCLE | STORY-SRS-ORD-006 | Sprint 5 | SRS-ORD-006 | MUST | System | Route order to owning bounded context via event/RPC without database coupling. | Downstream system acknowledges idempotently. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order lifecycle | FEAT-W1-ORD-ORDER-LIFECYCLE | STORY-SRS-ORD-007 | Sprint 5 | SRS-ORD-007 | MUST | Clinician | Specify clinical indication/reason when required by order type. | Required indication blocks submit until provided. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Orders and CPOE | FEAT-W1-ORD-ORDERS-AND-CPOE | STORY-SRS-ORD-008 | Sprint 5 | SRS-ORD-008 | MUST | System | Capture requested timing, frequency, priority and conditional instructions using structured fields. | Downstream receives normalized timing. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order lifecycle | FEAT-W1-ORD-ORDER-LIFECYCLE | STORY-SRS-ORD-009 | Sprint 5 | SRS-ORD-009 | MUST | System | Detect duplicate active orders using configurable type-specific rules and show warning rather than arbitrary suppression. | Clinician can review existing order and override where allowed. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order cancellation | FEAT-W1-ORD-ORDER-CANCELLATION | STORY-SRS-ORD-010 | Sprint 5 | SRS-ORD-010 | MUST | System | Audit all order placement/modification/cancellation with reason where required. | Audit links to originating user and client. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order cancellation | FEAT-W1-ORD-ORDER-CANCELLATION | STORY-SRS-ORD-011 | Sprint 5 | SRS-ORD-011 | MUST | System | Emit order.placed/accepted/in_progress/completed/cancelled events. | Events are versioned/idempotent. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.cancel | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-ORD | SRS-ORD | Order sets | FEAT-W1-ORD-ORDER-SETS | STORY-SRS-ORD-012 | Sprint 5 | SRS-ORD-012 | SHOULD | Clinician | Save favorites/personalized order panels without changing institutional order-set governance. | Personal preferences cannot bypass mandatory rules. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; Clinical Core; orderable catalog | orders | OrderService | ord.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Prescribing | FEAT-W1-MED-PRESCRIBING | STORY-SRS-MED-001 | Sprint 5 | SRS-MED-001 | MUST | Clinician | Prescribe structured medication with ingredient/product, dose, unit, route, frequency/timing, duration/stop condition, indication and instructions. | Prescription is machine-readable and human-readable. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Medication safety | FEAT-W1-MED-MEDICATION-SAFETY | STORY-SRS-MED-002 | Sprint 5 | SRS-MED-002 | MUST | System | Evaluate allergies/intolerances against medication terminology mapping before order confirmation. | Potential match produces severity-classified warning with rule/version. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-DAT | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Medication safety | FEAT-W1-MED-MEDICATION-SAFETY | STORY-SRS-MED-003 | Sprint 5 | SRS-MED-003 | MUST | System | Evaluate configured drug-drug interaction and duplicate-therapy rules. | Clinician sees interacting medications and may override only when policy permits. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.configure | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Dose / sig | FEAT-W1-MED-DOSE-SIG | STORY-SRS-MED-004 | Sprint 5 | SRS-MED-004 | MUST | System | Support renal/hepatic/pediatric dose-support rules as advisory CDS when configured and validated. | Inputs and rule/version are shown; final prescribing authority remains clinician. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.configure | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Medication reconciliation | FEAT-W1-MED-MEDICATION-RECONCILIATIO | STORY-SRS-MED-005 | Sprint 5 | SRS-MED-005 | MUST | Clinician | Perform medication reconciliation at admission, transfer and discharge. | Each home medication has continue/stop/change/unknown disposition. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Prescription verification | FEAT-W1-MED-PRESCRIPTION-VERIFICATIO | STORY-SRS-MED-006 | Sprint 5 | SRS-MED-006 | MUST | Pharmacist | Verify medication order before dispensing/administration when policy requires. | Verification status and pharmacist identity stored. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.verify | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Medication Management | FEAT-W1-MED-MEDICATION-MANAGEMENT | STORY-SRS-MED-007 | Sprint 5 | SRS-MED-007 | MUST | System | Generate eMAR administrations only from eligible medication orders. | Discontinued order prevents future administrations after effective stop time. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Dose / sig | FEAT-W1-MED-DOSE-SIG | STORY-SRS-MED-008 | Sprint 5 | SRS-MED-008 | MUST | Clinician | Support PRN medication with indication, minimum interval and maximum dose constraints. | eMAR enforces minimum interval/max dose policy where structured. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Dose / sig | FEAT-W1-MED-DOSE-SIG | STORY-SRS-MED-009 | Sprint 5 | SRS-MED-009 | MUST | Clinician | Support tapering/complex schedules via explicit dose segments. | Each segment is visible to nurse/pharmacist and versioned. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Dose / sig | FEAT-W1-MED-DOSE-SIG | STORY-SRS-MED-010 | Sprint 5 | SRS-MED-010 | MUST | System | Prevent ambiguous free-text-only dose for medication classes configured as requiring structured dose. | Submit is blocked until structured dose completed. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.configure | VP-SAF | Tier 0 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Prescribing | FEAT-W1-MED-PRESCRIBING | STORY-SRS-MED-011 | Sprint 5 | SRS-MED-011 | MUST | Pharmacist | Record substitution proposal/dispense product separately from prescribed product. | Substitution authorization and reason retained. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.write | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Medication Management | FEAT-W1-MED-MEDICATION-MANAGEMENT | STORY-SRS-MED-012 | Sprint 5 | SRS-MED-012 | MUST | System | Maintain formulary status and restrictions by facility/department/payer where configured. | Non-formulary choice shows policy action/approval path. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.configure | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Medication Management | FEAT-W1-MED-MEDICATION-MANAGEMENT | STORY-SRS-MED-013 | Sprint 5 | SRS-MED-013 | MUST | Clinician | Discontinue/hold/restart with effective time and reason. | Historical MAR remains unchanged; future schedule updates. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-MED | SRS-MED | Prescribing | FEAT-W1-MED-PRESCRIBING | STORY-SRS-MED-014 | Sprint 5 | SRS-MED-014 | MUST | System | Emit medication.prescribed/verified/held/discontinued/administered events. | Consumers can reconstruct medication timeline without mutating source ledger. | Wave 0 tenant/IAM/API/data/security foundation; Patient allergies; Orders; medication master | medication | MedicationService | med.manage | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Charge capture | FEAT-W1-BIL-CHARGE-CAPTURE | STORY-SRS-BIL-001 | Sprint 5 | SRS-BIL-001 | MUST | Finance Admin | Maintain service/charge master with code, description, department, tax attributes, revenue mapping and effective dates. | Historical invoice resolves service version active at charge time. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Tariff / pricing | FEAT-W1-BIL-TARIFF-PRICING | STORY-SRS-BIL-002 | Sprint 5 | SRS-BIL-002 | MUST | Finance Admin | Maintain tariff contracts by payer/customer/facility/room class/service and effective dates. | Pricing engine resolves deterministic applicable tariff. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.execute | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Charge capture | FEAT-W1-BIL-CHARGE-CAPTURE | STORY-SRS-BIL-003 | Sprint 5 | SRS-BIL-003 | MUST | System | Create charge from eligible clinical/operational event or authorized manual entry with source reference. | Every charge has source/provenance and cannot be silently duplicated. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.create | VP-SAF | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Billing, Tariffs and Patient Revenue | FEAT-W1-BIL-BILLING-TARIFFS-AND-PATI | STORY-SRS-BIL-004 | Sprint 5 | SRS-BIL-004 | MUST | System | Support package/bundle pricing with inclusions, exclusions, quantity caps and carve-outs. | Package consumption ledger explains billed/not billed items. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Estimate | FEAT-W1-BIL-ESTIMATE | STORY-SRS-BIL-005 | Sprint 5 | SRS-BIL-005 | MUST | Billing User | Create estimate using planned services/package and payer information. | Estimate is labeled non-final and versioned. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.create | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Invoice | FEAT-W1-BIL-INVOICE | STORY-SRS-BIL-006 | Sprint 5 | SRS-BIL-006 | MUST | Billing User | Create interim/final invoice from charge ledger. | Final invoice stores immutable line snapshot and calculation details. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.create | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Billing, Tariffs and Patient Revenue | FEAT-W1-BIL-BILLING-TARIFFS-AND-PATI | STORY-SRS-BIL-007 | Sprint 5 | SRS-BIL-007 | MUST | Billing User | Apply concession/discount only within authorization limits and reason. | Over-limit request routes for approval. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.manage | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Payment collection | FEAT-W1-BIL-PAYMENT-COLLECTION | STORY-SRS-BIL-008 | Sprint 5 | SRS-BIL-008 | MUST | Cashier | Receive payment with method/provider reference and allocate to invoice/account. | Receipt number atomic; payment event idempotent. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.execute | VP-FUN | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Refund / reversal | FEAT-W1-BIL-REFUND-REVERSAL | STORY-SRS-BIL-009 | Sprint 5 | SRS-BIL-009 | MUST | Cashier | Process refund/reversal referencing original payment and authorization. | Original payment retained; refund creates separate ledger entry. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.execute | VP-SEC | Tier 1 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Invoice | FEAT-W1-BIL-INVOICE | STORY-SRS-BIL-010 | Sprint 5 | SRS-BIL-010 | MUST | System | Prevent direct destructive edit of finalized invoice/receipt. | Correction uses credit/debit/reversal workflow. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.update | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Charge capture | FEAT-W1-BIL-CHARGE-CAPTURE | STORY-SRS-BIL-011 | Sprint 5 | SRS-BIL-011 | MUST | System | Identify unbilled completed services and pending charge exceptions. | Revenue-integrity worklist links to source record. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Refund / reversal | FEAT-W1-BIL-REFUND-REVERSAL | STORY-SRS-BIL-012 | Sprint 5 | SRS-BIL-012 | MUST | System | Support patient deposit/advance and consume/refund with auditable ledger. | Balance derives from ledger and reconciles. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Billing, Tariffs and Patient Revenue | FEAT-W1-BIL-BILLING-TARIFFS-AND-PATI | STORY-SRS-BIL-013 | Sprint 5 | SRS-BIL-013 | MUST | Billing User | Close encounter financial account only after configured reconciliation checks. | Blocking exceptions are listed. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.configure | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Billing, Tariffs and Patient Revenue | FEAT-W1-BIL-BILLING-TARIFFS-AND-PATI | STORY-SRS-BIL-014 | Sprint 5 | SRS-BIL-014 | MUST | System | Support split liability across patient/payer/corporate after adjudication. | Each balance has responsible party and provenance. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.execute | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Billing, Tariffs and Patient Revenue | FEAT-W1-BIL-BILLING-TARIFFS-AND-PATI | STORY-SRS-BIL-015 | Sprint 5 | SRS-BIL-015 | SHOULD | Finance | Support cashier shift/open-close and cash reconciliation. | Variance requires reason and approval per threshold. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.manage | VP-FUN | Tier 2 | TBD | Architecture/SRS mapped | Planned
EPIC-W1-BIL | SRS-BIL | Refund / reversal | FEAT-W1-BIL-REFUND-REVERSAL | STORY-SRS-BIL-016 | Sprint 5 | SRS-BIL-016 | MUST | System | Emit charge.posted, invoice.finalized, payment.received, refund.completed events. | Events reference financial objects without exposing unnecessary payment secrets. | Wave 0 tenant/IAM/API/data/security foundation; Encounter; charge catalog/tariff | billing | BillingService | bil.execute | VP-FUN | Tier 1 | TBD | Architecture/SRS mapped | Planned

## Sprint Plan
Sprint | Outcome | Primary Families | Exit Gate | Notes
Sprint 0 | Wave-0 prerequisites / skeleton | W0 | A1–A12 foundation gate progression | Runs in parallel before/with Wave 1
Sprint 1 | Patient identity skeleton | EMPI | Registration/search baseline + tenant/auth/audit | First end-to-end trace
Sprint 2 | EMPI completion | EMPI | Match/merge/identifier/relationship scenarios | Wrong-patient negative cases
Sprint 3 | Appointment/check-in/queue | SCH | Book/reschedule/cancel/check-in/queue | Reception vertical slice
Sprint 4 | Encounter + clinical/nursing | ENC/CLN/NUR | Start/close encounter; signed note; nursing foundation | Clinical validation
Sprint 5 | Orders + meds + billing | ORD/MED/BIL | Order/prescription/invoice/payment skeleton | Complete OPD vertical slice

## Dependencies
Dependency | Needed By | Owner | Acceptance
Wave-0 IAM/tenant context | Sprint 1 | Platform | Authenticated tenant/facility context reaches use case
Patient identity DB/proto skeleton | Sprint 1 | Core Clinical | Registration/search contract and repositories available
Design-system AppShell/PatientBanner | Sprint 1 | UX | Reusable shell passes accessibility baseline
Terminology placeholder/catalog interfaces | Sprint 4 | Enterprise Platform | Clinical codes bind without hard-coded UI strings
Orderable/medication/charge catalogs | Sprint 5 | Domain teams | Versioned reference records available
Test trace framework | Sprint 1 | Quality | Requirement ↔ test ↔ build evidence recorded
Tenant-isolation security harness | Sprint 1 | Security/QA | Cross-tenant negative tests reusable by all features
Pre-production deployment pipeline | Sprint 3 | SRE | Wave-1 vertical slice deployable with telemetry/rollback